## Project Tracker
Project Tracker
| Percent Over/Under to Flag: | 25%
Project | Category | Assigned To | Estimated Start | Estimated Finish | Estimated Work (in hours) | Estimated Duration (in days) | Actual Start | Actual Finish | Flag icon for Over/Under Actual Work (in hours) | Actual Work (in hours) | Flag icon for Over/Under Actual Duration (in days) | Actual Duration (in days) | Notes
Project 1 | Category 1 | Employee 1 | 2022-09-24 | 2022-11-23 | 210 | 59 | 2022-09-24 | 2022-11-28 | 1 | 300 | 0 | 64
Project 2 | Category 2 | Employee 4 | 2022-10-18 | 2022-11-18 | 400 | 30 | 2022-10-18 | 2022-11-21 | 0 | 390 | 0 | 33
Project 3 | Category 1 | Employee 2 | 2022-08-20 | 2022-10-19 | 500 | 59 | 2022-08-20 | 2022-11-01 | 0 | 500 | 0 | 71
Project 4 | Category 2 | Employee 3 | 2022-08-30 | 2022-09-09 | 250 | 9 | 2022-08-30 | 2022-09-18 | 0 | 276 | 1 | 18
Project 5 | Category 3 | Employee 2 | 2022-08-30 | 2022-10-09 | 300 | 39 | 2022-08-30 | 2022-10-15 | 0 | 310 | 0 | 45
Project 6 | Category 4 | Employee 4 | 2022-09-29 | 2022-10-09 | 500 | 10 | 2022-09-29 | 2022-10-14 | 0 | 510 | 1 | 15
Project 7 | Category 5 | Employee 1 | 2022-10-15 | 2022-11-08 | 750 | 23 | 2022-10-15 | 2022-11-13 | 0 | 790 | 0 | 28
Project 8 | Category 2 | Employee 1 | 2022-10-20 | 2022-11-28 | 450 | 38 | 2022-10-14 | 2022-11-23 | 0 | 430 | 0 | 39
project 9 | Category 4 | Employee 1 | 2016-02-05 | 2016-06-09 | 250 | 124 | 2016-03-05 | 2016-05-05 | 0 | 200 | 1 | 60
SETUP

## Setup
Setup
Category Name | Employee Name
Category 1 | Employee 1
Category 2 | Employee 2
Category 3 | Employee 3
Category 4 | Employee 4
Category 5 | Employee 5
Category 6 | Employee 6
PROJECTS

## Sheet1
Our Lady of the Holy Spirit Dec. 18, 2022 - Jan. 29, 2023
| Sunday | Christmas EVE | Christmas DAY | Sunday | Sunday | Sunday | Sunday | Sunday
| Dec. 18 | Dec. 24 | Dec. 25 | Jan. 1 | Jan. 8 | Jan. 15 | Jan. 22 | Jan. 29
Greeters | E. Alford | Ed/Pat Cirks | unassigned | M. Beck | E. Alford | Ed/Pat Cirks | M. Beck | Knights
Ushers | M. Elder | A. Ballweg | M. Elder | O. Baker | A. Ballweg | J. Langen | B. Bradley | Knights
| J. Langen | B. Bradley | J. Langen | B. Bradley | M. Elder | O. Baker | M. Elder
5:30 Usher | S. Leo | na | na | S. Leo | S. Leo | S. Leo | S. Leo | Knights
Servers | J. Baker | E. Becker | S. Driscoll | E. Miller | E. Smith | T. Alford | J. Baker | Knights
| V. Baker | C. Bradley | P. Driscoll | G. Miller | G. Smith | T. Alford | V. Baker
5:30 Server | B. Behm | na | na | L. Kralik | T. Kralik | B. Behm | L. Kralik | Knights
Lectors | E. Fritzsche | B. Ballweg | J. Mudd | M. Beck | A. Ballweg | B. Ballweg | D/V Goebel | Knights
| J. Gould | R. Plankenhorn | E. Alford | E. Becker | E. Fritzsche | R. Plankenhorn
5:30 Lector | S. Leo | na | na | J. Gould | S. Leo | J. Mudd | S. Leo | Knights
AUDITORS: Auditing is done once after 5:30 mass. Remember you do not have to go to that mass to audit, just count after it.
After 5:30 Mass | M. Elder | S. Jones | J. Mudd | B. Miller | A. Elder | J. Mudd | A. Elder | M. Elder
| B. Miller | D. Scales | E. Westjohn | D. Scales | S. Jones | D. Scales | B. Miller | S. Jones
| E. Westjohn | J. Mudd | A. Elder | M. Elder | E. Westjohn | B. Miller | E. Westjohn | J. Mudd
|  | *after 4pm mass | *after 9am mass
Sacristans: Mary Ann Beck, Laurie Cox, Vicky Wooten
PLEASE NOTE: IF YOU ARE UNABLE TO DO YOUR MINISTRY, YOU ARE TO FIND A REPLACEMENT FROM THE ENCLOSED LIST