## Project Tracker
Project Tracker
| Percent Over/Under to Flag: | 25%
Project | Category | Assigned To | Estimated Start | Estimated Finish | Estimated Work (in hours) | Estimated Duration (in days) | Actual Start | Actual Finish | Flag icon for Over/Under Actual Work (in hours) | Actual Work (in hours) | Flag icon for Over/Under Actual Duration (in days) | Actual Duration (in days) | Notes
Project 1 | Category 1 | Employee 1 | 2023-02-19 | 2023-04-20 | 210 | 61 | 2023-02-19 | 2023-04-25 | 1 | 300 | 0 | 66
Project 2 | Category 2 | Employee 4 | 2023-03-15 | 2023-04-15 | 400 | 30 | 2023-03-15 | 2023-04-18 | 0 | 390 | 0 | 33
Project 3 | Category 1 | Employee 2 | 2023-01-15 | 2023-03-16 | 500 | 61 | 2023-01-15 | 2023-03-29 | 0 | 500 | 0 | 74
Project 4 | Category 2 | Employee 3 | 2023-01-25 | 2023-02-04 | 250 | 9 | 2023-01-25 | 2023-02-13 | 0 | 276 | 1 | 18
Project 5 | Category 3 | Employee 2 | 2023-01-25 | 2023-03-06 | 300 | 41 | 2023-01-25 | 2023-03-12 | 0 | 310 | 0 | 47
Project 6 | Category 4 | Employee 4 | 2023-02-24 | 2023-03-06 | 500 | 12 | 2023-02-24 | 2023-03-11 | 0 | 510 | 1 | 17
Project 7 | Category 5 | Employee 1 | 2023-03-12 | 2023-04-05 | 750 | 23 | 2023-03-12 | 2023-04-10 | 0 | 790 | 0 | 28
Project 8 | Category 2 | Employee 1 | 2023-03-17 | 2023-04-25 | 450 | 38 | 2023-03-11 | 2023-04-20 | 0 | 430 | 0 | 39
project 9 | Category 4 | Employee 1 | 2016-02-05 | 2016-06-09 | 250 | 124 | 2016-03-05 | 2016-05-05 | 0 | 200 | 1 | 60
SETUP

## Setup
Setup
Category Name | Employee Name
Category 1 | Employee 1
Category 2 | Employee 2
Category 3 | Employee 3
Category 4 | Employee 4
Category 5 | Employee 5
Category 6 | Employee 6
PROJECTS

## Sheet1
St. Isidore - May 28 -July 16, 2023
| Sunday | Sunday | Sunday | Sunday | Sunday | Sunday | Sunday | Sunday
| May 28 | June 4 | June 11 | June 18 | June 25 | July 2 | July 9 | July 16
Greeters | L. McCabe | M. Martina | K. Bolsen | R.Brust | JC Fitzgerald | S. Fitzgerald | T. Fitzgerald | T. Jeffers
Ushers | D. McCabe | M. Reedy | T. Fitzgerald | M. Reedy | JC Fitzgerald | D. McCabe | R. Brust | T. Fitzgerald
| M. Reedy | JC Fitzgerald | D. McCabe | R. Brust | T. Fitzgerald | M. Reedy | JC Fitzgerald | D. McCabe
Server | M. Martina | D. Smith | M. Martina | D. Smith | M. Martina | D. Smith | M. Martina | D. Smith
Lector | L. Fitzgerald | A. Ballweg | K. Jeffers | D. McCabe | M. Reedy | A. Ballweg | L. Fitzgerald | K. Jeffers
Counter | D. Samples | D. Smith | JC Fitzgerald | T. Fitzgerald | D. McCabe | D. Samples | D. Smith | JC Fitzgerald
Please Note: If you are unable to fulfill your ministry date, please find a replacement. Thank you